## PMR
LOCAL GOVERNMENT UNIT OF LASAM, CAGAYAN | [9 empty] | Procurement Monitoring Report as of MARCH 30, 2026
[5 empty] | Actual Procurement Activities | [13 empty] | ABC (PhP) |  |  | Contract Cost (PhP) |  |  |  | Date of Receipt of Invitation
Code (PAP) | Procurement Project | PMO/End-User | Is this an Early Procurement Activity? | Mode of Procurement | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance | Source of Funds | Total | MOOE | CO | Total2 | MOOE2 | CO3 | List of Invited Observers | Pre-bid Conf4 | Eligibility Check5 | Sub/ Open of Bids6 | Bid Evaluation7 | Post Qual8 | Delivery/ Completion/ Acceptance (If applicable) | Remarks (Explaining changes from the APP)
COMPLETED PROCUREMENT ACTIVITIES
1 06 06 010 | Purchase of 1 Unit Brand New Excavator Crawler Type YC25 0.7 CBM for Excavation Purposes at New Public Cemetery | MEO | No | Competitive Bidding | 20/1/2026 | 21/1/2026 | 28/1/2026 | 2026-03-02 | 2026-04-02 | 2026-04-02 | 2026-05-02 | 2026-05-02 | 2026-06-02 | 2026-10-02 | 2026-12-02 | 13/3/2026 | 13/06/2026 | Capital Outlay Saving | 2200000 |  | 2200000 | 2190000 |  | 2190000 | LATODA President Senior Citizens Federation President | 23/1/2026 | NA | 29/1/2026 | NA | 29/1/2026
5 02 03 010 | Purchase of Various Office Supplies for 1st Quarter C.Y. 2026 | MA | No | Competitive Bidding | 21/1/2026 | 22/1/2026 | 28/1/2026 | 2026-04-02 | 2026-05-02 | 2026-05-02 | 2026-06-02 | 2026-06-02 | 2026-09-02 | 2026-10-02 | 2026-12-02 | 27/2/2026 | 27/2/2026 | Genral Fund | 360697 | 360697 |  | 354922 | 354922 |  | LATODA President Senior Citizens Federation President | 23/1/2026 | NA | 29/1/2026 | NA | 30/1/2026 |  | Purchase request has been amended by End Users and some items were purchaased at PS-DBM
1 06 03 010 | Road Opening and Gravelling of Farm to Market Road at Zone 03, Malinta, Lasam, Cagayan | MEO | No | Competitive Bidding | 30/01/2026 | 31/01/2026 | 2026-10-02 | 17/02/2026 | 18/02/2026 | 18/02/2026 | 19/02/2026 | 19/02/2026 | 20/02/2026 | 23/02/2026 | 25/02/2026 | 27/03/2026 | 27/03/2026 | 20% Development Fund | 500000 |  | 500000 | 497152.08 |  | 497152.08 | LATODA President Senior Citizens Federation President | 2026-05-02 | NA | 13/2/2026 | NA | 13/2/2026
1 06 03 010 | Road Opening and Concreting at Zone 03, Centro 03, Lasam, Cagayan | MEO | No | Competitive Bidding | 30/01/2026 | 31/01/2026 | 2026-10-02 | 17/02/2026 | 18/02/2026 | 18/02/2026 | 19/02/2026 | 19/02/2026 | 20/02/2026 | 23/02/2026 | 25/02/2026 | 2026-11-04 | 13/4/2026 | 20% Development Fund | 500000 |  | 500000 | 497177.78 |  | 497177.78 | LATODA President Senior Citizens Federation President | 2026-05-02 | NA | 13/2/2026 | NA | 13/2/2026
1 06 03 010 | Concreting of Barangay Extension Road at Zone 06 & 07, Calapangan Norte, Lasam, Cagayan | MEO | No | Competitive Bidding | 30/01/2026 | 31/01/2026 | 2026-10-02 | 17/02/2026 | 18/02/2026 | 18/02/2026 | 19/02/2026 | 19/02/2026 | 20/02/2026 | 23/02/2026 | 25/02/2026 | 2026-11-04 | 13/4/2026 | 20% Development Fund | 500000 |  | 500000 | 499977.08 |  | 499977.08 | LATODA President Senior Citizens Federation President | 2026-05-02 | NA | 13/2/2026 | NA | 13/2/2026
1 06 03 010 | Concreting of Farm to Market Road at Zone 01, 03 & 05, Aggunetan, Lasam, Cagayan | MEO | No | Competitive Bidding | 30/01/2026 | 31/01/2026 | 2026-10-02 | 17/02/2026 | 18/02/2026 | 18/02/2026 | 19/02/2026 | 19/02/2026 | 20/02/2026 | 23/02/2026 | 25/02/2026 | 2026-11-04 | 13/4/2026 | 20% Development Fund | 500000 |  | 500000 | 498792.1 |  | 498792.1 | LATODA President Senior Citizens Federation President | 2026-05-02 | NA | 13/2/2026 | NA | 13/2/2026
1 06 03 040 | Installation of Jetmatic Pumps-Phase VII at Lasam, Cagayan | MEO | No | Competitive Bidding | 30/01/2026 | 31/01/2026 | 2026-10-02 | 17/02/2026 | 18/02/2026 | 18/02/2026 | 19/02/2026 | 19/02/2026 | 20/02/2026 | 23/02/2026 | 25/02/2026 | 26/5/2026 | 27/5/2026 | 20% Development Fund | 1000000 |  | 1000000 | 997385.25 |  | 997385.25 | LATODA President Senior Citizens Federation President | 2026-05-02 | NA | 13/2/2026 | NA | 13/2/2026
1 06 03 010 | Concreting of Sanitary Landfill Access Road Phase II at Minanga Norte, Lasam, Cagayan | MEO | No | Competitive Bidding | 30/01/2026 | 31/01/2026 | 2026-10-02 | 17/02/2026 | 18/02/2026 | 18/02/2026 | 19/02/2026 | 19/02/2026 | 20/02/2026 | 23/02/2026 | 25/02/2026 | 26/5/2026 | 27/5/2026 | 20% Development Fund | 2000000 |  | 2000000 | 1997259.8 |  | 1997259.8 | LATODA President Senior Citizens Federation President | 2026-05-02 | NA | 13/2/2026 | NA | 13/2/2026
5 02 12 030 | Desilting of Tucalan Creek at Magsaysay-Tucalan Passing, Lasam, Cagayan | MEO | No | Competitive Bidding | 30/01/2026 | 31/01/2026 | 2026-10-02 | 17/02/2026 | 18/02/2026 | 18/02/2026 | 19/02/2026 | 19/02/2026 | 20/02/2026 | 23/02/2026 | 25/02/2026 | 2026-11-04 | 13/4/2026 | 20% Development Fund | 1000000 |  | 1000000 | 999529.38 |  | 999529.38 | LATODA President Senior Citizens Federation President | 2026-05-02 | NA | 13/2/2026 | NA | 13/2/2026
5 02 03 080 | Purchase of Various Medical Supplies for 1st Quarter C.Y. 2026 | MHSO | No | Competitive Bidding | 2026-09-02 | 2026-10-02 | 17/02/2026 | 23/02/2026 | 24/02/2026 | 24/02/2026 | 25/02/2026 | 25/02/2026 | 26/02/2026 | 27/02/2026 | 2026-02-03 | 17/3/2026 | 17/3/2026 | Genral Fund | 439565 | 439565 |  | 439000 | 439000 |  | LATODA President Senior Citizens Federation President | 13/02/2026 | NA | 19/02/2026 | NA | 20/02/2026
1 06 05 030 | Purchase of IT Equipment fro MDRRM Office and Operations Center | MDRRMO | No | Small Value Procurement | N/A | 13/3/2026 | N/A | N/A | 19/3/2026 | 19/3/2026 | N/A | 23/03/2026 | 23/03/2026 | 25/03/2026 | N/A | 28/03/2026 | 28/03/2026 | DRRM-GF | 203581 | 203581 |  | 203355 | 203355
1 06 06 010 | Purchase of 1 Unit Brand New Motor Vehicle(Van) with Ambulance Set-up | MDRRMO | No | Competitive Bidding | 2026-09-03 | 2026-10-03 | 17/03/2026 | 23/03/2026 | 24/03/2026 | 24/03/2026 | 25/03/2026 | 25/03/2026 | 26/03/2026 | 30/03/2026 | 2026-01-04 | 16/04/2026 | 16/04/2026 | DRRM-GF | 2500000 |  | 2500000 | 2497400 |  | 2497400 | LATODA President Senior Citizens Federation President | 2026-11-03 | NA | 19/03/2026 | NA | 19/03/2026
1 06 06 010 | Procurement of Trike for Disaster Monitoring and Response | MDRRMO | No | Small Value Procurement | N/A | 24/03/2026 | N/A | N/A | 27/03/2026 | 27/03/2026 | N/A | N/A | 2026-06-04 | N/A | N/A | 22/04/2026 | 22/04/2026 | DRRM Fund(Trust) | 360000 |  | 360000 | 359900 |  | 359900
1 06 05 030 | Procurement of 1 Unit Laptop for Office Use | Auditing Unit | No | Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 18/03/2026 | 18/03/2026 | General Fund(Auditing) | 50000 | 50000 |  | 49995 | 49995
1 06 05 070 | Purchase of 1 unit LCD Projector | MHSO | No | Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 22/01/2026 | 22/01/2026 | General Fund | 30000 | 30000 |  | 19300 | 19300
5 02 99 030 | Purchase of Snacks for Philhealth Validation of Metal Health Program for YAKAP Accreditation | MHSO | No | Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 30/01/2026 | 30/01/2026 | General Fund | 650 | 650 |  | 650 | 650
5 02 99 030 | Purchase of Meals and Snacks for TB Caravan | MHSO | No | Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 29/01/2026 | 29/01/2026 | General Fund | 14000 | 14000 |  | 14000 | 14000
5 02 99 030 | Purchase of Meals and Snacks for FHSIS Roll-Out Training | MHSO | No | Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 29/01/2026 | 29/01/2026 | General Fund | 28400 | 28400 |  | 28400 | 28400
1 06 05 030 | Purchase of 1 Unit Laptop for Office Use | MAO | No | Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-10-02 | 2026-10-02 | General Fund | 85000 |  | 85000 | 80000 |  | 80000
1 06 05 030 | Procurement of 1 Unit Laptop for Office Use | MBO | No | Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 21/01/2026 | 21/01/2026 | General Fund | 150000 |  | 150000 | 150000 |  | 150000
1 06 05 090 | Equipage and Procurement of search and rescue, emegercy medical service supplies | MDRRMO | No | Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-07-04 | 2026-07-04 | DRRM-GF | 57600 |  | 57600 | 57450 | 57450 | [8 empty] | Charge form DRRM regular supplies in their APP
5 02 03 080 | Payment of multivitamins of Solid Waste Action Team | MENRO | No | Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 27//03/2026 | 27//03/2026 | General Fund | 9000 | 9000 |  | 7200 | 7200 | [8 empty] | Charge from Office supplies of MENRO submiited at MA
5 02 03 050 | Purchase of Meals and Snacks for BHW Roll-Out on Notifiable Disease | MHSO | No | Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-03-02 | 2026-03-02 | General Fund | 9250 | 9250 | 9250 | 9250 | 9250
1 06 05 030 | Procurement of Laptop for Office Use | MHSO | No | Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 20/01/2026 | 20/01/2026 | General Fund | 60000 |  | 60000 | 60000 |  | 60000
5 02 03 050 | Meals and Snacks for MDRRMC and Cluster Group Meeting | MDRRMO | No | Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 30/03/2026 | 30/03/2026 | DRRM-GF | 3912 | 3912 |  | 3912 | 3912 | [8 empty] | Charge form DRRM regular supplies in their APP
1 06 07 010 | Procurement of Furniture for MDRRM Office and Operations Center | MDRRMO | No | Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 16/03/2026 | 16/03/2026 | General Fund | 113300 |  | 113300 | 106502 |  | 106502
1 06 07 010 | Procurement of Municipal Tricycle Plates | SBO(Secretrait) | No | Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 20/4/2026 | 20/4/2026 | General Fund | 27000 | 27000 |  | 26500 | 26500
1 06 05 020 | Purchase of Mini Refrigerator and Water Dispenser with Gallon | MHSO | No | Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-09-02 | 2026-09-02 | General Fund | 19500 | 19500 |  | 19250 | 19250
1 06 05 030 | Purchase of Electronic Tablet | MAO | No | Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 27/04/26 | 27/04/26 | General Fund | 30000 | 30000 |  | 29000 | 29000
1 06 05 020 | Purchase of 2 Units Printer | MBO | No | Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 15/05/2026 | 15/05/2026 |  | 60000 | 60000 |  | 43980 | 43980
1 06 05 020 | Purchase of 2 Units Printer | SEF(San Pedro Elem) | No | Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-04-05 | 2026-04-05 |  | 18000 | 18000 |  | 18000 | 18000
1 06 05 070 | Purchase of 1 Unit Sound System | SBO(Secretrait) | No | Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 20/05/2026 | 20/05/2026 |  | 30000 | 30000 |  | 30000 | 30000
1 04 04 990 | Purchase of Various Materials for RCA Extension | MENRO | No | Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 28/05/2026 | 28/05/2026 | Trust Fund | 223000 | 223000 |  | 220833 | 220833
1 04 04 060 | Purchase of Various Supplies Malaria Insecticide Spraying | MHSO | No | Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 30/03/2026 | 30/03/2026 | General Fund | 147250 | 147250 |  | 147250 | 147250
5 02 03 080 | Purchase of Various Medical Supplies for 2nd Quarater C.Y. 2026 | MHSO | No | Competitive Bidding | 2026-04-05 | 2026-05-05 | 13/05/2026 | 22/05/2026 | 25/05/2026 | 25/05/2026 | 26/05/2026 | 26/05/2026 | 2026-01-06 | 2026-02-06 | 2026-03-06 | 2026-08-06 | 2026-08-06 | General Fund | 455210 | 455210 |  | 454910 | 454910 | [8 empty] | based on submitted Purchased Request by End User
1 06 03 010 | Concreting of Farm to Market Road at Zone 06, San Pedro, Lasam, Cagayan | MEO | No | Competitive Bidding | 2026-05-05 | 2026-06-05 | 14/05/2026 | 25/05/2026 | 26/05/2026 | 26/05/2026 | 27/05/2026 | 28/05/2026 | 2026-01-06 | 2026-03-06 | 2026-04-06 |  |  | 20% Development Fund | 500000 |  | 500000 | 497948.67 |  | 497948.67
1 06 03 010 | Concreting of Farm to Market Road at Zone 04, New Orlins, Lasam, Cagayan | MEO | No | Competitive Bidding | 2026-05-05 | 2026-06-05 | 14/05/2026 | 25/05/2026 | 26/05/2026 | 26/05/2026 | 27/05/2026 | 28/05/2026 | 2026-01-06 | 2026-03-06 | 2026-04-06 |  |  | 20% Development Fund | 500000 |  | 500000 | 498637.94 |  | 498637.94
1 06 04 010 | Construction of Community Youth Learning Center Phase II at Centro 02, Lasam, Cagayan | MEO | No | Competitive Bidding | 2026-05-05 | 2026-06-05 | 14/05/2026 | 25/05/2026 | 26/05/2026 | 26/05/2026 | 27/05/2026 | 28/05/2026 | 2026-01-06 | 2026-03-06 | 2026-04-06 |  |  | 20% Development Fund | 2000000 |  | 2000000 | 1998474.11 |  | 1998474.11
1 06 04 010 | Rehabilitation of Barangay Gymnasium at Peru, Lasam, Cagayan | MEO | No | Competitive Bidding | 2026-05-05 | 2026-06-05 | 14/05/2026 | 25/05/2026 | 26/05/2026 | 26/05/2026 | 27/05/2026 | 28/05/2026 | 2026-01-06 | 2026-03-06 | 2026-04-06 |  |  | 20% Development Fund | 500000 |  | 500000 | 496816.81 |  | 496816.81
1 06 03 010 | Concreting of Access Road at P. Atienza Street, Nabannagan West, Lasam, Cagayan | MEO | No | Competitive Bidding | 2026-05-05 | 2026-06-05 | 14/05/2026 | 25/05/2026 | 26/05/2026 | 26/05/2026 | 27/05/2026 | 28/05/2026 | 2026-01-06 | 2026-03-06 | 2026-04-06 |  |  | 20% Development Fund | 500000 |  | 500000 | 498423.33 |  | 498423.33
1 06 03 010 | Concreting of Access Road at Zone 02, Minanga Sur, Lasam, Cagayan | MEO | No | Competitive Bidding | 19/5/2026 | 20/5/2026 | 28/5/2026 | 2026-08-06 | 2026-09-06 | 2026-09-06 | 2026-10-06 | 2026-10-06 | 2026-11-06 | 15/6/2026 | 16/6/2026 |  |  | 20% Development Fund | 500000 |  | 500000 | 498646.28 |  | 498646.28
1 06 03 010 | Concreting of Farm to Market Road at Zone 07, Alannay, Lasam, Cagayan | MEO | No | Competitive Bidding | 19/5/2026 | 20/5/2026 | 28/5/2026 | 2026-08-06 | 2026-09-06 | 2026-09-06 | 2026-10-06 | 2026-10-06 | 2026-11-06 | 15/6/2026 | 16/6/2026 |  |  | 20% Development Fund | 500000 |  | 500000 | 498662.27 |  | 498662.27
1 06 03 010 | Concreting of Farm to Market Road at Magsaysay, Lasam, Cagayan | MEO | No | Competitive Bidding | 19/5/2026 | 20/5/2026 | 28/5/2026 | 2026-08-06 | 2026-09-06 | 2026-09-06 | 2026-10-06 | 2026-10-06 | 2026-11-06 | 15/6/2026 | 16/6/2026 |  |  | 20% Development Fund | 500000 |  | 500000 | 497771.37 |  | 497771.37
1 06 03 010 | Concreting of Farm to Market Road at Zone 03, Battalan, Lasam, Cagayan | MEO | No | Competitive Bidding | 19/5/2026 | 20/5/2026 | 28/5/2026 | 2026-08-06 | 2026-09-06 | 2026-09-06 | 2026-10-06 | 2026-10-06 | 2026-11-06 | 15/6/2026 | 16/6/2026 |  |  | 20% Development Fund | 500000 |  | 500000 | 497669.72 |  | 497669.72
1 06 03 010 | Concreting of Access Road at Lasam Public Market, Centro 02, Lasam, Cagayan | MEO | No | Competitive Bidding | 19/5/2026 | 20/5/2026 | 28/5/2026 | 2026-08-06 | 2026-09-06 | 2026-09-06 | 2026-10-06 | 2026-10-06 | 2026-11-06 | 15/6/2026 | 16/6/2026 |  |  | 20% Development Fund | 2000000 |  | 2000000 | 1966106.55 |  | 1966106.55
1 06 03 010 | Concreting of Access Road at Zone 06, Ignacio B. Jurado, Lasam, Cagayan | MEO | No | Competitive Bidding | 19/5/2026 | 20/5/2026 | 28/5/2026 | 2026-08-06 | 2026-09-06 | 2026-09-06 | 2026-10-06 | 2026-10-06 | 2026-11-06 | 15/6/2026 | 16/6/2026 |  |  | 20% Development Fund | 500000 |  | 500000 | 498609.53 |  | 498609.53
[18 empty] | Total Allotted Budget of Procurement Activities | 22184915 | 2159015 | 20035150
[18 empty] | Total Contract Price of Procurement Activities Conducted |  |  |  | 22055999.05 | 2177157 | 19878842.05
[18 empty] | Total Savings (Total Allotted Budget - Total Contract Price) | 128915.95
Code (PAP) | Procurement Project | PMO/End-User | Is this an Early Procurement Activity? | Mode of Procurement | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance | Source of Funds | Total | MOOE | CO | Total2 | MOOE2 | CO3 | List of Invited Observers | Pre-bid Conf4 | Eligibility Check5 | Sub/Open of Bids6 | Bid Evaluation7 | Post Qual8 | Delivery/ Completion/ Acceptance (If applicable) | Remarks (Explaining changes from the APP)
ONGOING PROCUREMENT ACTIVITIES
| Construction of Bagsakan Center at Centro 02, Lasam, Cagayan | MEO | No | Competitive Bidding | 30/01/2026 | 31/01/2026 | 2026-10-02 | 17/02/2026 | 18/02/2026 | 18/02/2026 | 19/02/2026 | 19/02/2026 | 20/02/2026 | 23/02/2026 | 25/02/2026 | 2026-06-08 | 2026-06-08 | 20% Development Fund | 3790545.94 |  | 3790545.94 | 3787323.47 |  | 3787323.47 | LATODA President Senior Citizens Federation President | 2026-05-02 | NA | 13/2/2026 | NA | 13/2/2026
[18 empty] | Total Allotted Budget of On-going Procurement Activities | 3790545.94 | 0 | 3790545.94 | 3787323.47 | 0 | 3787323.47
|  | Prepared by: | [5 empty] | 2026-05-02: Recommended for Approval by: | [6 empty] | APPROVED:
|  | MELCHOR O. QUINTO, JR. | [5 empty] | 2026-05-02: JOSE A. REBULTAN, JR. | [6 empty] | ENGR. DANTE DEXTER A. AGATEP
|  | BAC Secretariat | [5 empty] | 2026-05-02: BAC Chairperson | [6 empty] | Head of the Procuring Entity

## Sheet1
Project Title | End-User or Implementing Unit | Is this an Early Procurement Activity? | Mode of Procurement | Delivery | Inspection/acceptance | Amount
|  | No | Direct Acquisition
Procurement of 1 Unit Laptop for Office Use | Auditing Unit | No | Direct Acquisition
Purchase of 1 unit LCD Projector | MHSO | No | Direct Acquisition
Purchase of 1 Unit Laptop for Office Use | MAO | No | Direct Acquisition
Procurement of 1 Unit Laptop for Office Use | MBO | No | Direct Acquisition

## Validation Menu (hidden)
REMARKS | STATUS | STAGE OF PROCUREMENT | Source of Funds | Mode of Procurement
Awarded with issued Notice of Award | Awarded | Invitation To Bid | Government of the Philippines (current year's budget) | Competitive Bidding
Completed | Completed | Pre-bidding Conference | Government of the Philippines (continuing budget) | Limited Source Bidding
Ongoing Procurement Process | Failed | Opening of Bids | Government of the Philippines (current year's and continuing budget) | Direct Contracting
Failed under Section 32.2.1 (a) | Ongoing | Bid Evaluation | Grant by an International Financing Institution | Repeat Order
Failed under Section 35.1 (a) |  | Post-Qualification | Loan from an International Financing Institution | Shopping 52.1(a) - Unforeseen Contingency
Failed under Section 35.1 (b) |  | BAC Resolution |  | Shopping 52.1(b) - Regular Office Supplies and Equipment not available in PS
Failed under Section 35.1 (c) |  | Award |  | Negotiated Procurement - Two Failed Biddings
Failed under Section 41 (b) |  | Cancelled |  | Negotiated Procurement - Emergency Cases
Failed under Section 41 (c) |  |  |  | Negotiated Procurement - Take-Over of Contracts
Contract was extended |  |  |  | Negotiated Procurement - Adjacent or Contiguous
Contract was renewed |  |  |  | Negotiated Procurement - Agency-to-Agency
Cancelled |  |  |  | Negotiated Procurement - Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services
Others, please encode directly on the cell |  |  |  | Negotiated Procurement - Highly Technical Consultants
Negotiated Procurement - Defense Cooperation Agreement
Negotiated Procurement - Small Value Procurement
Negotiated Procurement - Lease of Real Property and Venue
Negotiated Procurement - NGO Participation
Negotiated Procurement - Community Participation
Negotiated Procurement - UN Agencies, Int'l Organizations or International Financing Institutions
Negotiated Procurement - Direct Retail Purchase of Petroleum Fuel, Oil and Lubricant Products, Electronic Charging Devices, and Online Subscriptions
Foreign Guidelines - Competitive Bidding
Foreign Guidelines - Alternative Method
Competitive Dialogue
Unsolicited Offer with Bid Matching
Direct Acquisition
Direct Sales
Direct Procurement for Science, Technology, and Innovation
Others, specify in the remarks: Mode of Procurement use <Mode>